## Current Iteration
|  | Iteration Number: |  |  |  | 4
|  | Expected Total effort: |  |  |  | 38
|  | Days In Sprint: |  |  |  | 10
Burndown Chart
User Stories |  | Days (Net Points Completed) | [19 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
0
create the basic web page() | [21 empty] | 0
Explore Maven: Create a simple Maven project to understand its structure and functionality (Vinnicius). | 4 | Days (Net Points Completed) 1: 1; Days (Net Points Completed) 2: 0; Days (Net Points Completed) 3: 1 | 2 | 50%
Learning about React/Angular for the frontend (Daniel) | 8 | Days (Net Points Completed) 1: 2; Days (Net Points Completed) 2: 1; Days (Net Points Completed) 3: 1; Days (Net Points Completed) 4: 4 | 0 | 100%
Create the GitHub Repository (Vinnicius) | 2 | [20 empty] | 0 | 100% | bar: Days (Net Points Completed) 1 to Days (Net Points Completed) 2
Choose and set up a backend language (Vinnicius and Xueli) | 4 | [20 empty] | 2 | 50% | bar: Days (Net Points Completed) 2 to Days (Net Points Completed) 3
Establish a basic server and API structure (Xueli) | 2 | [20 empty] | 0 | 100% | bar: Days (Net Points Completed) 2; Days (Net Points Completed) 4
Begin designing the database schema (Vinnicius and Xulie) | [21 empty] | 0
Learn what is required and how things work together. (Sowby) | 12 | Days (Net Points Completed) 1: 3; Days (Net Points Completed) 2: 0; Days (Net Points Completed) 3: 0; Days (Net Points Completed) 4: 6 | 3 | 75%
Create wireframe (Johan) | 6 | Days (Net Points Completed) 1: 2; Days (Net Points Completed) 2: 1; Days (Net Points Completed) 3: 0; Days (Net Points Completed) 4: 1 | 2 | 66.67%
Feature 11 | [21 empty] | 0
Setup Spring Boot | [21 empty] | 0
Setup React App | [21 empty] | 0
Base REST Controller | [21 empty] | 0
SQL Database Installation | [21 empty] | 0
Initial Entity Definition | [21 empty] | 0
Basic JPA Concepts | [21 empty] | 0
Simple Repository Creation | [21 empty] | 0
CRUD Endpoints | [21 empty] | 0
Service Implementation | [21 empty] | 0
Service-Repository Integration | [21 empty] | 0
Application Properties Setup | [21 empty] | 0
CRUD Operations Testing | [21 empty] | 0
Axios Setup | [21 empty] | 0
State Management | [21 empty] | 0
Component Design | [21 empty] | 0
Navigation Setup | [21 empty] | 0
Backend Authentication | [21 empty] | 0
Frontend Login/Logout | [21 empty] | 0
Feature 30 | [21 empty] | 0
Effort Remaining | 38 | 29 | 24 | 21 | 9 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 9 | 76.32%
Ideal Trend | 38 | 34.2 | 30.4 | 26.6 | 22.8 | 19 | 15.2 | 11.4 | 7.6 | 3.8 | - | - | - | - | - | - | - | - | - | - | -
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days

## Proposed Backlog Items
Task | Subtask | Description | Hours | Assigned To | Dependency
Environment Setup | Install IntelliJ IDEA | Download and install IntelliJ IDEA Community Edition. | 1 | All Members
Environment Setup | Install Node.js | Download and install Node.js LTS version. | 1 | All Members
Environment Setup | Install Maven | Download and install Maven and configure environment variables. | 1 | All Members
Environment Setup | Install Git | Download and install Git, set up basic configuration. | 1 | All Members
Project Structure | Setup Spring Boot | Initialize Spring Boot project structure in IntelliJ IDEA. | 2 | 3 | Install IntelliJ IDEA
Project Structure | Setup React App | Initialize React application using create-react-app. | 2 |  | Install Node.js
Project Structure | Base REST Controller | Implement a basic REST controller with a dummy endpoint. | 2 |  | Setup Spring Boot
Database Configuration | SQL Database Installation | Install a SQL database locally (e.g., MySQL, PostgreSQL). | 2 |  | Install Maven
Database Configuration | Initial Entity Definition | Define an initial set of entities for the project. | 2 |  | SQL Database Installation
JPA Learning | Basic JPA Concepts | Learn basic concepts and annotations of JPA. | 2
JPA Learning | Simple Repository Creation | Create a simple JPA repository for an initial entity. | 2 |  | Basic JPA Concepts
REST Enhancements | CRUD Endpoints | Implement CRUD operations in REST controller for an entity. | 4 |  | Base REST Controller
Business Logic | Service Implementation | Implement business logic for CRUD operations in service layer. | 4 |  | CRUD Endpoints
Business Logic | Service-Repository Integration | Ensure service layer properly interacts with JPA repository. | 4 |  | Service Implementation
Database Integration | Application Properties Setup | Configure application properties for the database connection. | 2 |  | SQL Database Installation
Database Integration | CRUD Operations Testing | Test database CRUD operations through JPA repository. | 2 |  | Application Properties Setup
Frontend Development | Axios Setup | Set up Axios in React app to make HTTP requests. | 2 |  | Setup React App
Frontend Development | State Management | Implement state management for API response handling. | 2 |  | Axios Setup
UI Development | Component Design | Design and implement basic UI components (e.g., event list). | 4 |  | Setup React App
UI Development | Navigation Setup | Implement navigation in the React app using React Router. | 2 |  | Component Design
Authentication | Backend Authentication | Implement user authentication mechanism in the backend. | 4 |  | Business Logic
Authentication | Frontend Login/Logout | Add login/logout UI and functionality in the frontend. | 4 |  | Backend Authentication
Map Feature | Map API Integration | Integrate a map API into the frontend. | 4 |  | Frontend Development
Map Feature | Display Event Markers | Display event markers on the map based on API data. | 4 |  | Map API Integration
Service Features | Filtering and Sorting | Add filtering and sorting logic in service layer. | 4 |  | Business Logic
Service Features | Pagination | Add pagination logic in service layer. | 2 |  | Filtering and Sorting
Error Handling | Backend Error Handling | Implement global error handling in the backend. | 3 |  | Business Logic
Error Handling | Frontend Error Display | Add user-friendly error responses in the frontend. | 3 |  | Backend Error Handling
Testing | REST Controller Testing | Write unit tests for REST controller methods. | 4